## Delivery Governance
Pillar 1: Engineering Health (Delivery Governance)
| KPI | How to Measure | Target | mpro | Ecomm | POSV/IVC | IBPS-Dolphin,POS,Claim
1 | Sprint Commitment | (Story Points Completed ÷ Story Points Committed) × 100 | >90%
2 | Release Success Rate | (Successful Releases ÷ Total Releases) × 100 | >98%
3 | Deployment Frequency | Number of deployments to UAT/Production per week/month | Increasing trend
4 | Team Capacity Utilization | Productive utilization of available capacity | >=90%
5 | AI Efficiency | Efficiency Gain (%) = ((Time Without AI - Time With AI) / Time Without AI) × 100 | 20 -30%(Brownfield ) 50-70%(Greenfield)

## KPIs
| KPI | How to Measure | Target |  | Apr |  |  |  |  | May |  |  |  |  | june
| Pillar 1: Engineering Health (Delivery Governance) |  |  | Source | mpro | Ecomm | IBPS | MS-Dolpin | IVC/POSV | mpro | Ecomm | MS-Dolphin | IBPS-Dolphin,POS,Claim | IVC/POSV | mpro | Ecomm | MS-Dolphin | IBPS-Dolphin,POS,Claim | IVC/POSV
| Sprint Commitment | (Story Points Completed ÷ Story Points Committed) × 100 | >90% | Jira | 82 | 85.3846 | 83.5165 | 83.5165 | 58.8235 | 81 | 85.3846 | 83.5165 | 83.5165 | 58.8235 | 81 | 85.3846 | 83.5165 | 83.5165 | 58.8235
| Release Success Rate | (Successful Releases ÷ Total Releases) × 100 | >98% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Deployment Frequency | Number of deployments to Production per month | Increasing trend |  | 2 | 5 | 2 | 2 | 2 | 2 | 7 | 2 | 2 | 2 | 2 | 6 | 2 | 2 | 2
| Team Capacity Utilization | Productive utilization of available capacity | >=90% |  | 120.311 | 106.5868 | 100.2381 | 124.5421 | 121.2121 | 118.0682 | 91.9492 | 114.6154 | 103.75 | 145 | 113.6213 | 99.2063 | 106.3492 | 105 | 108.658
| AI Efficiency | Efficiency Gain (%) = ((Time Without AI - Time With AI) / Time Without AI) × 100 | 20 -30%(Brownfield ) 50-70%(Greenfield) |  | 7.474% | 3.746% | 0% | 0% | 0% | 10.66% | 8.051% | 0% | 0% | 0% | 12.98% | 11.91% | 0% | 0% | 0%
Pillar 2: Engineering Quality
| Defect density | Total Number of Defects / SP | 0.3 – 0.5 |  |  | 0.26 |  |  |  |  | 0.3 |  |  |  | 0.11 | 0.17 | 0.11 |  | 0.11
| Test Automation Coverage | (Automated Test Cases ÷ Total Regression Test Cases) × 100 | >90%
| Unit Test Coverage | (Lines/Branches Covered ÷ Total Lines/Branches) × 100 | >90% |  | 20% |  |  |  |  | 20% |  |  |  |  | 30%
| Code Review Compliance | (PRs Reviewed Before Merge ÷ Total PRs) × 100 | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Technical Debt Backlog | Open technical debt items or technical debt days(SP) | Month-on-month reduction |  | 1053 | 877 | 658 | 353 | 348 | 983 | 827 | 330 | 618 | 300 | 912 | 770 | 303 | 600 | 262
| VAPT/security Compliance,DPDP | (Critical/High Vulnerabilities Closed within SLA ÷ Total Identified) × 100 | No of Open VAPT |  | 4 | 10 | 9 | 0 | 13 | 3 | 6 | 0 | 24 | 9 | 0 | 8 | 0 | 0 | 3
| EOL Compliance | Applications free from End-of-Life technologies | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Sustain
| system availability | Maintain optimal uptime with minimal infrastructure waste | >99.9% | Sustain Report | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99.83% | 100% | 100% | 99.96% | 100% | 99.88% | 100%
| Server/Cloud Utilization | Average utilization of compute resources | >75% | Dynatrace | 65% | 66% | 70% | 82% | 85% | 80% | 78% | 88% | 73% | 90% | 71% | 66% | 84% | 77% | 82%
| Production Defects/hypercare post release | Defects reported after production release | Zero Sev-1/Sev-2 | Sustain Report | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0
Production Defects/hypercare | Production Defects | Defects reported | Zero Sev-1/Sev-2 | Sustain Report | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-1 S3-1 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-2 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-1 S2-0 S3-0 | S1-0 S2-0 S3-0 | S1-0 S2-2 S3-1 | S1-0 S2-0 S3-0
| MTTR | Mean Time to Resolve production incidents(Sev-1/Sev-2) | <4 hours (Critical incidents) | Sustain Report | 0 Hr | 0 Hr | 2.1hr | 0 Hr | 0 Hr | 0 Hr | 0 Hr | 1.1hr | 0 Hr | 0 Hr | 0 Hr | 0.5 Hr | 0 Hr | 0 Hr | 0 Hr
COST
| Run/Cloud Cost | Cost and resource utilization efficiency score | Continuous improvement | AWS Cost report | 1297676.0811 | 1269233.9457 | 4073488.2036 | 485023.8613 | 357792.4481 | 1351494.1408 | 1516791.6683 | 423132.8725 | 3997524.4269 | 465743.8299
| Cost to build |  |  | Jira | 9100 | 10424 | 12933 | 7954 | 6926 | 9795.9533 | 12687.8959 | 13120.4819 | 9621.83 |  | 9421.835 | 10863.3466 | 12357.7165 | 8004.8759 | 7748
| Throughput(With AI) |  |  | Jira | 1338 | 1372 | 421 | 340 | 280 | 1163 | 1180 | 298 | 415 | 319 | 1179 | 1419 | 268 | 441 | 251
| Throughput (Jira time log) |  |  |  | 1238 | 1320.61 | 421 | 340 | 280 | 1039 | 1085 | 298 | 415 | 319 | 1026 | 1250 | 268 | 441 | 251
| Resource |  |  |  | 49 | 59 | 20 | 13 | 11 | 44 | 59 | 13 | 20 | 11 | 43 | 60 | 12 | 20 | 11

## Calculation
| total | Live |  |  |  | total | Live
Distribution | 52 | 10 | 19.2308
Dolphin | 90 | 75 | 83.3333 |  | POS
Falcon | 9 | 0 | 0 |  |  |  |  | 1180
INSIGHT | 51 | 37 | 72.549
Partnership | 51 | 15 | 29.4118 |  |  |  |  | 1085
Product Track | 37 | 0 | 0
POSV | 35 | 19 | 54.2857
Sprinter | 33 | 27 | 81.8182 |  |  |  |  | 95
Zest | 16 | 14 | 87.5
| 374 | 197 | 52.6738
|  |  | 7943 | 1238 | 9833434

## Quality
Pillar 2: Engineering Quality
| KPI | How to Measure | Target
1 | Defect density | Total Number of Defects / SP | 0.03 – 0.05
2 | Test Automation Coverage | (Automated Test Cases ÷ Total Regression Test Cases) × 100 | >90%
3 | Unit Test Coverage | (Lines/Branches Covered ÷ Total Lines/Branches) × 100 | >90% | UT and SIT ratio
4 | Code Review Compliance | (PRs Reviewed Before Merge ÷ Total PRs) × 100 | 100% | Automation AI
5 | Technical Debt Backlog | Open technical debt items or technical debt days | Month-on-month reduction | Target need to recheck
6 | VAPT/security Compliance,DPDP | (Critical/High Vulnerabilities Closed within SLA ÷ Total Identified) × 100 | 95%
| EOL Compliance | Applications free from End-of-Life technologies | 100%

## Automation
Pillar 3: Engineering Excellence & Automation
| KPI | How to Measure | Target
1 | Deployment Automation | (Automated Deployments ÷ Total Deployments) × 100 | >90%
2 | AI Adoption | (Developers Using Approved AI Tools ÷ Total Developers) × 100 | >80% | Effiecency,KPI review
3 | Monitoring Coverage | Applications with dashboards, logging and alerting | 100%

## Sustain
KPI | Definition | Target | mpro | Ecomm | POSV/IVC | IBPS-Dolphin,POS,Claim
system availability | Maintain optimal uptime with minimal infrastructure waste | >99.9%
Server/Cloud Utilization | Average utilization of compute resources | >75%
Production Defects/hypercare | Defects reported after production release | Zero Sev-1/Sev-2
MTTR | Mean Time to Resolve production incidents | <4 hours (Critical incidents)

## Cost
KPI | Definition | Target
Run/Cloud Cost | Cost and resource utilization efficiency score | Continuous improvement
Cost to build

## Sheet1
Parent Project | Application Name | Parent Requirement Name | Jira ID | Story Description | Story Type | Sprint-month | Story Points | Story Refinement Date | Dev Start Date | Dev End Date | Actual Effort (Hrs) | UAT Deployment Date | UAT Start Date | UAT End Date | UAT Status | Production Release Date | Production Completion Date | Production Status | Rollback (Y/N) | Rollback Reason | AI Used (Y/N) | Estimated Effort Without AI (Hrs) | Actual Effort With AI (Hrs) | Story Status | Story Drop Reason
Onboarding Transformation | Customer Onboarding | Digital Customer Onboarding | JIRA-101 | Create Customer API | Story | 2026-06-01 | 8 | 2026-01-01 | 2026-01-03 | 2026-01-08 | 32 | 2026-01-09 | 2026-01-09 | 2026-01-11 | Pass | 2026-01-15 | 2026-01-15 | Success | N | NA | Y | 48 | 32 | Completed | NA

## IBPS-POS
Sno | Project | Status | Items list | Walkthrough given on (To Dev team)-Date | JIRA ID | Estimated Effort Without AI (SP) | Dev Start | Dev End Date | Development Status | UAT Delivery Date | UAT Sign Off Date | GO Live planned Date | GO Live Date | Production Status | Rollback (Y/N) | Rollback Reason | AI Used (Y/N) | Estimated Effort Without AI (Hrs) | Actual Effort With AI (Hrs) | Story Status | Story Drop Reason
1 | Gift City | GO live | Address information update basis gift city indicator in letters | 2026-04-05 | IP-350 | 8 | 2026-04-07 | 2026-04-17 | Completed | 2026-04-20 | 2026-05-05 | 2026-05-07 | 2026-05-07 | GO live | N |  | N
2 | Gift City | GO live | ACR communication dollar sign change for "additional premium required" ACR reason | 2026-04-06 | IP-352 | 8 | 2026-04-08 | 2026-04-13 | Completed | 2026-04-13 | 2026-05-05 | 2026-05-07 | 2026-05-07 | GO live | N |  | N
3 | Brand Refresh | GO live | Logo change in IBPS application | 2026-04-16 | IP-363 | 3 | 2026-04-17 | 2026-04-21 | Completed | 2026-04-23 | 2026-05-05 | 2026-05-07 | 2026-05-07 | GO live | N |  | N
4 | POS STP 2 -NEFT update | GO live | NEFT update Salutation change | 2026-04-22 | PSI-156 | 6 | 2026-04-24 | 2026-05-01 | Completed | 2026-05-04 | 2026-05-18 | 2026-05-20 | 2026-05-20 | GO live | N |  | N
5 | POS STP 2 -NEFT update | GO live | Nationality & FATCA | 2026-04-23 | PSI-182 | 4 | 2026-04-24 | 2026-05-01 | Completed | 2026-05-05 | 2026-05-18 | 2026-05-20 | 2026-05-20 | GO live | N |  | N
6 | POS STP 2 -NEFT update | GO live | Replace “Decline” decision with “Transaction not done by API” in Comm Failure bucket for all worktypes ¦¦ | 2026-04-27 | PSI-219 | 2 | 2026-05-04 | 2026-05-06 | Completed | 2026-05-07 | 2026-05-18 | 2026-05-20 | 2026-05-20 | GO live | N |  | N
7 | POS STP 2 -NEFT update | GO live | IBPS workflow changes for existing BRMS rule change "Case NSTP due to Source Validation Failed" ¦¦ | 2026-04-27 | PSI-176 | 4 | 2026-05-04 | 2026-05-07 | Completed | 2026-05-11 | 2026-05-18 | 2026-05-20 | 2026-05-20 | GO live | N |  | N
8 | Services movement On prem to Cloud | GO live | 10 services needs to move from On prem to Cloud -30th apr | 2026-03-29 | IP-302 | 10 | 2026-04-01 | 2026-04-14 | Completed | 3 services (policy surrender , PAN , UW requirement reinstatement) credentials not available .. Support required from SOA | 2026-05-18 | 2026-05-20 | 2026-05-20 | GO live | N |  | N
9 | POS STP 2 -NEFT update | GO live | IBPS workflow changes for less than 40% score segment : basis Penny Drop failure scenario for NEFT Update worktype. | 2026-04-27 | PSI-175 | 7 | 2026-05-04 | 2026-05-12 | Completed | 2026-05-13 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
10 | POS STP 2 -6 worktypes | GO live | User Story for Placing Policy status based validation for "NEFT update" while login the request ¦¦ | 2026-04-27 | PSI-155 | 8 | 2026-05-08 | 2026-05-19 | Completed | 2026-05-20 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
11 | POS STP 2 -NEFT update | GO live | User story :IBPS workflow changes for disabling "Account number/IFSC code mismatch penny drop out-BRMS rule | 2026-05-10 | PSI-208 | 4 | 2026-05-13 | 2026-05-18 | Completed | 2026-05-20 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
12 | POS STP 2- Address change | GO live | Disabling "Annual premium based " Validation logic /BRMS rule in IBPS | 2026-05-15 | PSI-226 | 4 | 2026-05-20 | 2026-05-26 | Completed | 2026-05-29 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
13 | UNO-IBPS integration | GO live | Addition of emailid and phone number in createworkitem-UNO-IBPS | 2026-05-15 | IP-460 | 2 | 2026-05-20 | 2026-05-22 | Completed |  | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
14 | UNO-IBPS integration | GO live | Making goname as non mandatory in createwi -UNO-IBPS | 2026-05-23 | IP-459 | 2 | 2026-05-25 | 2026-05-26 | Completed |  | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
15 | POS STP 2 -NEFT update & Address change | GO live | Ekyc journey enablement for NEFT update worktype (POS STP 2) | 2026-05-15 | PSI-178 | 7 | 2026-05-19 | 2026-05-28 | Completed | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
16 | POS STP 2- Address change | GO live | Disabling "Nationality & FACTA validation" BRMS rule in IBPS | 2026-05-12 | PSI-227 | 4 | 2026-05-29 | 2026-06-03 | Completed | 2026-06-04 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
17 | Adhoc -Mspace | GO live | Request log in IBPS where Source or GO code name "mSpace" - Request coming through Mongo DB | 2026-05-29 | IP-489 | 2 | 2026-06-04 | 2026-06-05 | Completed | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
18 | Adhoc - CIP | GO live | Communication NPP mapping | 2026-05-29 | CIP-1754 | 1.5 | 2026-06-03 | 2026-06-04 | Completed | 2026-06-04 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
19 | Adhoc-uno ibps | GO live | TAG CONSUMPTION | 2026-05-29 | IP-494 | 1.5 | 2026-06-04 | 2026-06-05 | Completed | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-09 | GO live | N |  | N
20 | Person update & Switching of fund | Planned for 8th Jul | User story : for Bypass Policy Validation for policy type HUF / Employer–Employee /MWPA/Keyman policy type : for PAN update/ Person Update /Switching of fund¦¦ (PSI-256) | 2026-05-22 | PSI-256 | 3 | 2026-06-08 | 2026-06-10 | Completed | 2026-06-11 | 2026-07-06 | 2026-07-08 | 2026-07-08
21 | Person update | Planned for 8th Jul | User story :Restriction of Person Update Requests for Non–Max Life Assigned Policies (IBPS)” | 2026-05-22 | PSi-257 | 3 | 2026-06-11 | 2026-06-16 | Completed | 2026-06-16 | 2026-07-06 | 2026-07-08 | 2026-07-08
22 | NEFT update | Planned for 8th Jul | User Story: Enable Duplicate Check for NEFT Update Requests in IBPS ¦¦ PSI-165 | 2026-06-11 | PSI-165 | 4 | 2026-06-18 | 24-jun-26 | Completed | 2026-06-24 | 2026-07-06 | 2026-07-08 | 2026-07-08
23 | POS STP 2 -Address change | Planned for 8th Jul | POS WIP -AML child ticket - Footprint | 2026-06-11 | PSI-244 | 3 | 2026-06-17 | 2026-06-22 | Completed | 2026-06-22 | 2026-07-06 | 2026-07-08 | 2026-07-08
24 | POS OR item | Planned for 8th Jul | 2 worktypes workflow creation in Myflow : FGEP- CCMS final discussion on letter | 2026-06-16 | IP-526 + IP -587 | 2 | 2026-06-23 | 2026-06-24 | Completed | 2026-06-24 | 2026-07-06 | 2026-07-08 | 2026-07-08
25 | PAN & Person update | Planned for 8th Jul | User story : Disabling the BRMS rule - Nationality & FATCA validation failed’ & workflow change for PAN & Person Updation worktype ¦¦ | 2026-06-23 | PSI-255 | 2 | 2026-06-25 | 2026-06-29 | Completed |  | 2026-07-06 | 2026-07-08 | 2026-07-08
26 | Hawkeye Audit observation | Planned for 8th Jul | [IP-522] User story : Displaying Email ID on Case Layout for Dispatch Workstep ¦¦ - JIRA | 2026-06-16 | IP-522 | 4 | 2026-06-29 | 2026-07-03 | Completed | 2026-07-03 | 2026-07-06 | 2026-07-08 | 2026-07-08
27 | POS STP 2 -NEFT update | QA WIP item | Expanding ACR decision-making responsibility from POS Executive to Child Ticket users for NEFT update PSI-218 | 2026-04-27 | PSI-218 | 15 | 2026-05-25 | 6/15/2026 (dent of 3 days because of CIP-1574) | WIP | 6/15/2026 18-jun-26 | 2026-06-22 | September - planned in August , shifted to sep (dependency on PSI-220)
28 | PROJECT hAWKeye | DEV WIP item | POS wip and dashboard report password protection | 2026-06-16 | IP-451 | 10 | 2026-06-25 | 2026-07-08 | WIP | 2026-07-09 | 2026-07-10 | July
29 | POS STP 2- Address change | DEV WIP item | Ekyc journey enablement for Address change worktype (POS STP 2) | 2026-06-16 | PSI-285 | 7 | 2026-07-03 | 2026-07-10 | WIP | 2026-07-10 | 2026-07-10 | Aug
30 |  | DEV WIP item | Duplicate check - other than neft | 2026-06-16 | PSI-273 | 3 | 2026-07-13 | 2026-07-15 | WIP |  | 2026-07-16 | Aug
31 | POS STP 2 -NEFT update | DEV WIP item | Enable IBPS to send communication (all categories) triggers to CCMS +Additional effrts | 2026-05-25 | PSI-220 | 55 | 2026-05-29 | 2026-08-14 | WIP IN DEV | 2026-08-14 | 2026-08-14 | September
32 | POS STP 2- Address change | DEV WIP item | Expanding ACR decision-making responsibility from POS Executive to Child Ticket users for Address Change | 2026-07-13 | PSI-235 | 18 | 2026-07-16 | 2026-08-11 |  |  | 2026-08-11 | September
33 | POS STP 2-Person Update | DEV WIP item | User story : eKYC service enablement for "Person Update" worktype : In IBPS ¦¦ | 2026-07-08 | PSI-290 | 7 | 2026-07-10 | 2026-07-21 |  |  | 2026-07-21 | September
34 | POS STP 2-Nominee Change | DEV WIP item | User story : Expanding ACR decision-making responsibility to child Ticket users for Change of Nominee” worktype ¦¦ | 2026-07-18 | PSI-282 | 15 | 2026-07-22 | 2026-08-13 |  |  | 2026-08-13 | Aug
35 | POS STP 2-Person Update | DEV WIP item | User story : Expanding ACR decision-making responsibility Signature Child Ticket users for Person update” worktype ¦¦ | Walkthrough to schedule | PSI-283 | 12 | 2026-08-11 | 2026-08-27 |  |  | 2026-08-27 | September
36 | POS STP 2- Address change | DEV WIP item | Scrubing CCMS using Client ID for Address change | 2026-06-16 | PSI-289 | 5 | 2026-08-13 | 2026-08-20 |  |  | 2026-08-20 | September
37 | POS STP-Nominee change | DEV WIP item | User story : Restriction of Change in Nominee Requests for Non–Max Life Assigned Policies (POS STP 2)¦¦ | Walkthrough to schedule | PSI-238 | 3 | 2026-08-17 | 2026-08-21 |  |  | 2026-08-22 | September